| Proven Consulting | Proposal 16 SEPTEMBER 2026 |
| --- | --- |

| CLIENT Al Anwaar Al Anwaar Charity Group Ltd ABN 16 643 085 152 | ENGAGEMENT Donation platform New build, replacing the current site | DURATION 5 weeks 16 September to 20 October 2026 | STATUS For approval Commercials to be completed before issue |
| --- | --- | --- | --- |

| 1. Introduction |  |
| --- | --- |

Al Anwaar takes donations today through a WordPress shop, where every appeal is set up as a product, every gift is an order, and every bank transfer is matched by hand. That set up cannot hold a proper donor record, run a monthly plan, or keep track of whether a gift was zakat or sadaqah.

We will replace it with a platform built for a charity: a new website with a giving flow and a zakat calculator, a portal where donors look after their own giving, a portal where your team runs the charity, and the records and reports the ACNC expects. The build takes five weeks, from 16 September to 20 October 2026. Your current site stays live and untouched until the new one is up and working.

| 2. What we will build |  |
| --- | --- |

Stack: MERN (MongoDB, Express, React, Node)

| LAYER | WHAT WE USE | WHY THIS ONE |
| --- | --- | --- |
| Database | MongoDB, hosted on Atlas | A donor is not a neat row in a grid. One donor carries gifts, recurring plans, designations, receipts, bank matches and enquiries hanging off them. MongoDB keeps that as one record instead of six joined tables, and all three parts of the platform read the same record. |
| Backend and API | Node.js with Express | The server everything talks to. It holds the rules: who may see a donor, what goes on a receipt, when a recurring gift is taken, and what happens when a card is declined. |
| Frontend | React | The website, the donor portal and the admin portal are built from one set of React components, so a fix to the giving flow fixes it in every place at once. |
| Login and permissions | JSON Web Tokens, role based | Donors, staff and volunteers each get only the rights their role needs. A volunteer entering cash gifts cannot open the compliance registers or export your donor list. |
| Payments | Stripe and PayPal | Card giving through Stripe and PayPal giving through PayPal, both set up in Al Anwaar's own accounts. The money settles straight to you and we never hold it. |
| Email | Amazon SES/SMTP | Everything the platform sends out: receipts, thank yous, reminders, failed payment notices, annual tax statements, login codes and alerts to your team. |
| Files and images | Amazon S3 | Appeal photography, the media library behind the page builder, and the document library at section 2.6. |
| Hosting | AWS, with backups and SSL | Hosting, backups and the security certificate. Charged monthly and listed at section 4.3. |

2.1   The public website   What anyone visiting the site can see

Site structure. Every page below is built, written and set up to lead a visitor towards giving.

| Home | About us | Where the money goes | Our impact |
| --- | --- | --- | --- |
| Appeals | Ramadan (active when req.) | Dhul Hijjah (active when req.) | Zakat calculator |
| Get involved | Events | Stories | Gallery |
| Volunteer | Partners | Contact | Donate |

| Appeal pages | A page for each appeal, holding the story behind it, photos from the ground, how much has been raised against the target, and updates posted as the work goes on. When an appeal closes the page stays up as a record of what the money did. |
| --- | --- |
| Seasonal campaigns | Your busy periods are built before they arrive: the last ten nights of Ramadan, the ten days of Dhul Hijjah, and everyday giving. The pages and the amounts are ready in advance, so on the night itself nobody is putting a page together. |
| Zakat calculator | Takes what someone owns in cash, gold, silver and business stock, subtracts what they owe, checks it against the current nisab and tells them what is due. It then carries that amount straight into the donation page, so they are not left working out what to type. |
| Search visibility | The calculator also earns its keep outside Ramadan. People search for a zakat calculator all year, and it is the strongest way for a Muslim charity to bring in visitors who have never heard of you. Every page is also set up so search engines can read and list it. |
| Page builder | Your team edits any page, adds photos, saves a draft, previews it and publishes. Old versions are kept, so a mistake can be rolled back without ringing us. |
| Copywriting | We write the words for every page and every appeal from the material you give us. |
| Trust signals | Your ABN, DGR endorsement, registered charity status and secure payment marks are shown across the site. A first time donor can see at a glance that you are a real, registered charity. |
| Phones and accessibility | Built for phones first, because that is where most giving happens, and checked for accessibility so nobody is shut out of donating. |

2.2   Making a donation   The steps a donor goes through to give

There is no cart and no checkout. Giving is not shopping, so a donation is one short flow that most donors finish in under a minute.

| STEP 1 Pick an appeal From an appeal page, the zakat calculator, a campaign link or the donate button in the header. | → | STEP 2 Choose the amount Suggested amounts set per appeal, a box for any other amount, or items counted in units such as food packs, water tanks and Qurban shares. | → | STEP 3 Choose how often Once, weekly, fortnightly or monthly. A larger gift can be split into instalments instead. |
| --- | --- | --- | --- | --- |

| STEP 4 Add the details Name and email, what the gift is for (zakat, sadaqah, lillah, kaffarah or general), and the option to cover the fees or give anonymously. | → | STEP 5 Pay Card through Stripe, or PayPal, or a bank transfer using the account details and reference shown on screen. | → | STEP 6 Receipt and record The receipt is emailed within seconds, the appeal total moves, and the gift is saved against the donor's record. |
| --- | --- | --- | --- | --- |

| Paying by card | Card payments run through Stripe and PayPal payments through PayPal, both set up in Al Anwaar's own accounts. The money settles directly to you and we never hold it at any point. |
| --- | --- |
| Suggested amounts | Set per appeal, so a water appeal can offer $50, $150 and $500 while Qurban offers shares. Your team changes these whenever you like, without asking us. |
| Paying by bank transfer | Offered inside the same flow, with your account details and a unique reference shown on screen, so the gift can be found and matched when the transfer lands in your account. |
| What the gift is for | Every gift carries whether it is zakat, sadaqah, lillah, kaffarah or general. That label stays on the gift through to the reports, so you can always show how much zakat came in and where it went. |
| Regular giving | Weekly, fortnightly and monthly gifts are set up in the same flow and run on their own afterwards. The donor is emailed before each payment is taken, so nothing is a surprise. |
| Failed payments | If a card is declined the system tries again, emails the donor a link to fix it, and flags it to your team, instead of the plan quietly dying and the income disappearing. |
| Instalments | A large gift can be spread across a set number of payments, which suits Qurban and the bigger Ramadan gifts a donor cannot pay in one go. |
| Receipts | A tax deductible receipt carrying your ABN and DGR endorsement is emailed the moment the payment clears. Nobody on your team sends one by hand and no donor is left waiting. |
| Donation widget and links | A donation box you can paste into an email or a social media post, plus short links that open on one appeal with the amount already set, for your campaigns. |
| Fees and anonymity | Donors can choose to cover the payment fees so the whole gift reaches the appeal, and can choose to keep their name off any public list. |

2.3   The donor portal   Where your supporters log in and look after their own giving

| Giving history | Donors see every gift they have ever given, whether it came in by card, by bank transfer or in person at an event. It is one history, not a separate list per payment method. |
| --- | --- |
| Managing regular gifts | Their plans are listed with the next payment date. They can pause, change the amount, move to a different card or cancel themselves, at any hour, without ringing your office. |
| Receipts and tax statements | Any receipt can be emailed again with one press, and the whole financial year downloads as a single tax statement at the end of June, which is when most of these requests arrive. |
| Their own details | Donors keep their address, phone number and email up to date and choose which emails they want. Your records stay clean without your team typing anything in. |
| Fundraising pages | Supporters can start their own page for a wedding, a walk, a workplace appeal or a birthday, set a target, share the link and watch it fill. What they raise counts towards the appeal it belongs to. |
| Secure login | Protected by a one time code sent to the donor's email, and they can sign in with a Google or Facebook account instead of remembering another password. |

2.4   The admin portal   Where your team runs the charity day to day

| Donor records | One record for every donor, holding their details, every gift they have given, what each gift was for, and every email they have been sent. |
| --- | --- |
| Duplicates | When the same person appears twice, under two email addresses or two spellings, the system flags it and your team merges the two records into one without losing any history. |
| Appeals and campaigns | Set the target, write the story, choose when it opens and when it closes, and watch the total move. Closing an appeal stops new gifts but keeps the page and its history. |
| Approving fundraising pages | Pages started by supporters come into a queue for approval before they go public, so nothing appears in Al Anwaar's name that your team has not read first. |
| Email campaigns | Written from a template and sent to a group you choose, such as every monthly donor, everyone who gave to one country, or everyone who has not given for a year. They go out in batches so they arrive properly. |
| Enquiries and sign ups | Event sign ups, volunteer applications, partner enquiries and contact messages land here and attach to the person's donor record, so you see the whole relationship in one place. |
| Dashboard | What has been raised this month and this year, how much regular giving brings in, how each appeal is performing, and how many donors are new, returning or have stopped. |
| Staff access | Every staff member and volunteer gets their own login with only the access their role needs, and every action is recorded with the name and the time. |

2.5   Bank transfers and gifts given offline   Part of the admin portal, so online and offline sit together

Bank transfers are matched by hand today. This is the part that replaces that work.

| STEP 1 Upload Export the statement from your bank and upload the file to the admin portal. | → | STEP 2 Match The system reads each line and matches it to a donor and an appeal using the name and the reference. | → | STEP 3 Check Every match is shown on screen before anything is saved. Anything it is unsure about waits in a queue. | → | STEP 4 Confirm You press confirm. The gifts are saved to the donor records and the receipts go out by email. |
| --- | --- | --- | --- | --- | --- | --- |

| Preview before saving | Nothing is written to a donor record until someone has seen it. The preview step exists so a wrong match never reaches a donor or a receipt. |
| --- | --- |
| Unmatched queue | Gifts that cannot be matched, because the reference is missing or the name does not line up, sit in a queue until a person decides. The system never guesses quietly. |
| Cash, cheques and events | Gifts that arrive another way are entered by hand and attached to a donor in the same few clicks, so they are counted with everything else. |
| One receipt trail | Receipts and annual tax statements come out of the same record whichever way the money arrived, so a donor who gives by card and by transfer still gets one statement covering everything. |
| Income reports | Income by appeal, by what the gift was for, by country and by date range, exported for your accountant at the end of the year. |
| Xero export | An export in the shape Xero expects, so your bookkeeper is not re-typing donation figures from one system into another. |

2.6   Compliance and record keeping   Part of the admin portal, covering the ACNC standards that apply to you

| Registers | Responsible people, overseas partners, policies, risks and conflicts of interest, held in the system instead of spread across separate spreadsheets. |
| --- | --- |
| Statutory calendar | Everything that is due, each with a date, a person responsible and a place to keep the proof, covering the AIS, activity statements and fundraising notifications. Reminders go out by email before each one falls due. |
| Document library | Your auditor's compliance report, your policies and your partner agreements. Old versions are kept, and you can see who has read what. |
| Audit trail | Every action taken in the system is logged with the person and the time, and the whole log can be exported when an auditor or the ACNC asks for it. |
| Reports | On demand, covering receipts issued, income by appeal and designation, activity by country, and the action log. |

A note on compliance. The platform stores and reports on the records you already keep, and pulls the year's evidence together when you need it. Your auditor's compliance report is given to us and loaded in. We are a technology partner, not auditors or lawyers, and nothing in this proposal is legal, tax or audit advice.

| 3. Delivery Timeline | Five weeks, 16 Sep to 20 Oct 2026 |
| --- | --- |

Five weeks, starting Wednesday 16 September 2026 and finishing Tuesday 20 October 2026. Two weeks on the website and donations, two weeks on the two portals, and one week of testing and go live. We will build them in this order.

| WEEKS 1 AND 2 16 to 29 September 2026 | The website and donations We apply the Al Anwaar brand to the design and get it signed off, then build the whole public site: home, appeal pages, where the money goes, about us, get involved, events, stories and contact. The donation flow at section 2.2 is built from start to finish, along with the zakat calculator and its path through to giving. Seasonal appeals are set up. Stripe and PayPal are connected in test mode, your bank details are loaded, and the receipt email is set up with your ABN and DGR endorsement. We write and load the copy, and hand the page builder to your team. We need from you: Your logo and brand files, photos and video you have the rights to use, Stripe and PayPal accounts in the charity's name, and access to your domain. |
| --- | --- |
| WEEKS 3 AND 4 30 September to 13 October 2026 | The donor portal and the admin portal We build the donor portal: the account, giving history, active plans, receipts and the annual tax statement. Then the admin portal: donor records with duplicate merging, appeals and campaigns, supporter fundraising pages and their approval queue, email campaigns, events, volunteers, enquiries and the dashboard. Monthly plans and instalments are switched on. The bank import and the Xero export are set up. The compliance registers are created and filled. Staff logins and permissions are set. We need from you: Your existing donor and gift records to bring across, access to your bank and accounting, the auditor's compliance report, the details for the registers, and a list of the staff who need a login. |
| WEEK 5 14 to 20 October 2026 | Testing, training and go live Every way of giving is tested with real cards, including monthly plans, instalments and bank transfer. The wording on receipts and statements is checked before the first live donation. Your reviewers test the site against a written list, we fix whatever they find and test it again. We run a training session for whoever will look after the platform and leave written notes behind. Then we go live on your domain, with redirects from the old site, and the old site is retired once the new one is confirmed working. We need from you: Your reviewers available across the week, and their feedback back to us in time for us to fix things before go live. |

| 4. Commercials | Amounts to be completed before issue |
| --- | --- |

All amounts are in Australian dollars and exclude GST. The build fee is fixed for the work set out in section 2 and the five weeks in section 3.

4.1   Build fee   One off, fixed for the work at section 2

| ITEM | BASIS | AMOUNT (AUD, EX GST) |
| --- | --- | --- |
| The website and donations | Weeks 1 and 2, sections 2.1 and 2.2 | $ |
| The donor portal and the admin portal | Weeks 3 and 4, sections 2.3 to 2.5 | $ |
| Compliance and record keeping | Section 2.6 | $ |
| Testing, training and go live | Week 5 | $ |
| Writing the copy for all pages and appeals | Two rounds of changes included | $ |
| Total build fee | Payable against the milestones at 4.2 | $ |

4.2   Payment milestones   Invoiced on the day, payable within 7 days

| # | MILESTONE | SHARE | AMOUNT (AUD, EX GST) |
| --- | --- | --- | --- |
| 1 | When this proposal is signed off, at the start of week 1 | 40% | $ |
| 2 | When both portals are finished and testing starts, at the end of week 4 | 30% | $ |
| 3 | On go live and handover, at the end of week 5 | 30% | $ |

4.3   Ongoing, after go live   Agreed before signing

| ITEM | BASIS | AMOUNT (AUD, EX GST) |
| --- | --- | --- |
| Hosting, backups and SSL | Per month | $ |
| Platform licence and updates | Per month | $ |
| Support and maintenance | Per month, response times to be agreed | $ |
| Further work outside this proposal | Per hour, quoted and approved in writing first | $ |

Not included. The fees Stripe, PayPal or the bank charge on each payment; registering and renewing the domain; paid email delivery volume; stock photo or video licences; and any other subscription taken in Al Anwaar's own name. These are billed to Al Anwaar directly, or passed on at cost where we arrange them for you. This quotation is valid for 30 days from the date of issue.

| 5. Sign off |  |
| --- | --- |

Signing below approves the work at section 2, the timeline at section 3 and the commercials at section 4. Week one starts on the date of signature, or on 16 September 2026, whichever is later. Al Anwaar will name one person who can approve content and sign off each stage, and will give us the items listed against each stage in section 3 at the start of that stage.

| FOR AL ANWAAR Al Anwaar Charity Group Ltd, ABN 16 643 085 152 Name Position Signature Date | FOR PROVEN CONSULTING Proven Consulting Name Position Signature Date |
| --- | --- |

|  | PROVEN CONSULTING 16 SEPTEMBER 2026 |
| --- | --- |